## QHSE _Running Project Status
QHSE Project Database
Last Updated date: 15 Dec 2025 | [7 empty] | Legends Colour - Gray - Standard Informations, Blue - Quality Specific, Orange - Reporting
Sr No | Project No | Project Title | CLIENT | Project Manager | Project Starting Date | Project Closing Date | Project Extension | Project Quality Engineer | Manhours for Quality | Manhours Used | Manhours Balance | Quality Billability % | Project Quality Plan status - Rev | Project Quality Plan status - Issued Date | Project Audit -1 | Project Audit -2 | Project Audit -3 | Project Audit -4 | Client Audit -1 | Client Audit -2 | Delay in Audits - No. of Days | CARs Open | CARs Delayed closing No. days | CARs Closed | No. of Obs Open | Obs delayed closing No. of Days | Obs Closed | Project KPIs Achieved % | Project Compl. % | Rejection of Deliverables % | Cost of Poor Quality in AED | Remarks
1 | 5900738 | FEED + Engineering & Procurement Services and Construction Management (EPCM) for Grid Power Integration Project Das Island | ADNOC GAS | Pankaj Kumar | 27.11.2023 | 27.11.2026 |  | Rajasekhar | 238 | 154 | 84 | 64.71% | Rev. 1 | 17.09.2024 | 20.03.2024 | 11.09.2024 |  |  | 21.10.2024 |  | 0 | 0 | 0 | 2 | 0 | 0 | 11 | 100% | 100 | 1.51 | 4500 | Lastest KPI : Sep 2024
2 | 5900885 | HABSHAN & BAB TELECOM SYSTEMS UPGRADE PROJECT | ADNOC GAS | Pravin Kumar | 05.01.2024 | 05.01.2025 | 18.01.2025 | Rajasekhar |  |  |  | #REF! | Rev. A | 03.04.2024 | 23.05.2024 | 08.08.2024 | 05.11.2024 |  | 19.01.2024 | 21.08.2024 | 0 | 0 | 0 | 2 | 0 | 0 | 24 | 83.33% | 98.26 | 0.55 | 10500 | The contractual project completion date of 15-January-2025 is expired. Lastest KPI : Mar 2025
3 | 5900891 | Details Engineering for KEZAD Gas Network Phase 3 | Al Fanar & Abu Dhabi Ports - KEZAD | Muddaser | 11.03.2024 | 12.08.2024 |  | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 2 | 23.05.2024 | 16.05.2024 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 9 | 80% | 97.91 | 0.52 | 4200 | Project Closing Date is expired and client extention date was not recived. Lastest KPI : Mar 2025
4 | 5900828 | Migration of AVEVA Models to Smart Plant | ADNOC GAS | Praveen Yeledahalli | 08.04.2024 | 08.04.2026 |  | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 0 | 16.10.2024 | 11.02.2025 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7 |  | 39.71 | 0.72 | 5400
5 | 5900837 | Debottlenecking of Steam Condensate System in Habshan – 5 | ADNOC GAS | Pravin Kumar | 16.05.2024 | 16.01.2025 | 31.10.2025 | Ravikumar | 60 | 23 | 37 | 38.33% | Rev. 0 | 27.09.2024 | 23.07.2025 | 12.11.2025 |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 34 | 8 |  | 92.36 | 1.25 | 4500 | Lastest KPI : Mar 2025
6 | 5900803 | FALCOR Battery Systems DAS Island Project | Falcor/ ADNOC OFFSHORE | Pravin Kumar | 15.08.2023 | 14.04.2024 | 30.06.2025 | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 2 | 01.09.2023 | 30.Jan.24 | 23.Aug.24 | 18.Apr.25 |  |  |  | 0 | 0 | 0 | 4 | 0 | 0 | 13 |  | 88.43 | 2.91 | 18100 | Extension is expired. Lastest KPI : Mar 2025
7 | 5900737 | FEED for Upgrade of Train 1 & 2 Fire and Gas Detection System & F&G Mapping Study for LNG and ASR Trains | ADNOC GAS | Pravin Kumar | 12.10.2023 | 11.10.2024 | 27.03.2025 | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 0 | 11.12.2023 | 12.2023 | 2.2024 | 7.2024 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75% | 99.11 | 7.55 | 0 | Extension is expired. Lastest KPI : Mar 2025
8 | 5900921 | Operator Shelter Improvement Project | ADNOC Refining | Ossi Valto | 08.05.2024 | 30.10.2024 | 30.10.2025 | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 0 | 26.06.2024 | 09.08.2024 |  |  |  | 24.09.2024 |  | 0 | 0 | 0 | 8 | 0 | 0 | 24 |  | 92.54 | 4.46 | 14100 | Lastest KPI : Mar 2025
9 | 5900892 | Ruwais NGL Train-3 Fire & Gas Detection Mapping Implementation | ISCCO / ADNOC GAS | Muddaser | 05.06.2024 | 05.12.2024 | 16.12.2024 | Rajasekhar | 14 | 78 | -64 | 557.1% | Rev. 0 | 27.08.2024 | 06.09.2024 | 23.10.2024 |  |  | 15.09.2024 | 29.10.2024 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 100% | 98.34 | 0.17 | 900 | Client Audit -3: 08.01.2025 Extension is expired. Lastest KPI : Nov 2024 Project Control Engineer is saying that the project is closed but documents are still rivewed by the client
10 | 5900878 | FEED for C&F Instrument Air Piping Network Replacement / Upgrade at DAS island | ADNOC OFFSHORE | Ossi Valto | 03.06.2024 | 03.03.2025 | 15.05.2025 | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 3 | 26.09.2024 | 19.08.2024 | 02.10.2024 | 22.11.2024 | 24.01.2025 | [10 empty] | 98.34 | 0.22 | 1500 | PROJECT COMPLETED
11 | 5900913 | Residue Yield Improvement Project | ADNOC Refining | Pankaj Kumar | 10.06.2024 | 26.11.2025 |  | Rajasekhar | 175 | 135 | 40 | 77.14% | Rev. 0 | 19.12.2024 | 22.04.2025 | 6.2025 | 7.2025 | 8.2025 |  |  | 0 | 0 | 0 | 4 | 0 | 0 | 8 |  | 33.71 | 1.43 | 11400 | Lastest KPI : July 2025
12 | 5900942 | Upgradation works at AL AIN MP Depot and RAK Depot | ADNOC DISTRIBUTION | Pravin Kumar | 15.07.2024 | 21.11.2024 | 25.05.2025 | Ravikumar |  |  | 0 | #DIV/0! | Rev. 3 | 14.11.2024 | 09.09.2024 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6 |  | 83.97 | 0 | 0 | PROJECT COMPLETED
13 | 5900935 | FEED Project – BAB MISCELLANEOUS WORKS – PACKAGE 1 | ADNOC ONSHORE | Pravin Kumar | 27.08.2024 | 26.02.2025 | 30.09.2025 | Ravikumar |  |  | 0 | #DIV/0! | Rev. 3 | 09.01.2025 | 07.01.2025 | 28.03.2025 | 10.06.2025 |  |  |  | 0 | 0 | 0 | 4 | 2 | 263 | 25 | 88.89% | 94.96 | 1.02 | 33700 | Lastest KPI : Jun 2025
14 | 5900978 | TRAIN 3 DECOUPLING MODIFICATIONS (APS) | ADVANCED PETRO SERVICES / ADNOC GAS | Ossi Valto | 02.09.2024 | 02.12.2024 |  | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 1 | 06.12.2024 | [15 empty] | 0.63 | 900 | PROJECT COMPLETED
15 | 5900899 | LASER SCAN AND PROVISION OF FULL INTELLIGENT 3D MODELS FOR DAS ISLAND | ADNOC GAS | Praveen Yeledahalli | 16.08.2024 | 16.02.2027 |  | Ravikumar |  |  | 0 | #DIV/0! | Rev. 0 | 17.09.2024 | [14 empty] | 39.71 | 0 | 0
16 | 5900970 | Demolition of Tanks at Madinat Zayed Depot & RAK Depot | ADNOC DISTRIBUTION | Pravin Kumar | 30.09.2024 | 18.01.2025 | 12.09.2025 | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 3 | 11.12.2024 | 06.12.2024 | [5 empty] | 0 | 0 | 0 | 0 | 6 | 375 | 0 | 75% | 95.19 | 0 | 0 | PROJECT COMPLETED
17 | 5900982 | DIVERT EXCESS MP FUEL GAS-HABSHAN 0 | DESCON / ADNOC GAS | Muddaser | 23.09.2024 | 23.03.2025 |  | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 0 | 08.11.2024 | 03.01.2025 | 27.03.2025 | 09.06.2025 |  | 15.09.2024 | 28.10.2024 | 0 | 0 | 0 | 2 | 2 | 156 | 14 |  | 98.34 | 1.73 | 15600 | Project Closing Date is expired and client extention date was not recived. Lastest KPI : Dec 2024 Note all internal audit dates are incorrects as well as the number of CARS & Observations please double check.
18 | 5900983 | H5 FLARES UPGRADE OF IGNITION AND DETECTION SYSTEMS | DESCON / ADNOC GAS | Muddaser | 23.09.2024 | 23.02.2025 |  | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 0 | 27.12.2024 | 14.01.2025 | 25.04.2025 | 09.06.2025 |  |  |  | 0 | 0 | 0 | 2 | 0 | 0 | 13 |  | 78.21 | 6.1 | 5700 | Project Closing Date is expired and client extention date was not recived. The Audit reports are not found inside the progect folder as well as the audit scheduale.
19 | 5900996 | STUDY ENERGY_PROCESS IMPROVEMENTS_SUSTAINABILITY INITIATIVES | ADNOC GAS | Pankaj Kumar | 16.10.2024 | 30.04.2025 | 30.06.2025 | Ravikumar |  |  | 0 | #DIV/0! | NA | [15 empty] | 78.79 | 0 | 0 | PROJECT COMPLETED
20 | 5900974 | FEED for Replacement of Switchgears in ACPT1 and ACPT 2 in UZ | ADNOC OFFSHORE | Pravin Kumar | 15.12.2024 | 15.08.2025 |  | Rajasekhar | 76 | 142 | -66 | 186.8% | Rev. C1 | 23.05.2025 | 27.05.2025 | 10.07.2025 | 01.09.2025 |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 18 |  | 96.63 | 0 | 0 | Lastest KPI : May 2025
21 | 5900863 | EPC FOR BOROUGE EU3 H2 EXTRACTION UNIT PROJECT | DESCON /Borouge | Pankaj Kumar | 25.11.2024 | 24.09.2025 |  | Jawaher |  |  | 0 | #DIV/0! | Rev. Q | 01.08.2025 | 18.June.25 |  |  |  | 30.May.25 |  | 0 | 0 | 0 | 0 | 3 | 151 | 21 | 100% | 56.55 | 1.55 | 21200 | Lastest KPI : Jun 2025
22 | 5900936 | Construction of Permanent Outstations in Zirku Plant Area | SAT / ADNOC OFFSHORE | Ossi Valto | 20.12.2024 | 20.06.2025 | 23.09.2025 | Rajasekhar | 62 | 62 | 0 | 100% | Rev. A1 | 13.01.2025 | 31.03.2025 | 09.07.2025 |  |  | 31.07.2025 |  | 0 | 0 | 0 | 0 | 6 | 260 | 9 |  | 77.78 | 2.34 | 6800 | Lastest KPI : May 2025
23 | 5900985 | EPC FOR PE4 & PE5 REVAMP PROJECT | TARGET / Borouge | Muddaser Moazzam | 26.12.2024 | 24.04.2026 |  | Jawaher |  |  | 0 | #DIV/0! | Rev. 3 | 09.01.2025 | 24.Jun.25 | 30.09.2025 |  |  | 26.Jun.25 |  | 0 | 0 | 0 | 1 | 10 | 142 | 3 | 83.33% | 61.42 | 1.21 | 48100 | Lastest KPI : Jun 2025
24 | 5900988 | Rerating of Vapor Recovery Compressor & Modifications | ADNOC Gas | Pankaj Kumar | 05.02.2025 | 04.09.2025 |  | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 0 | 14.04.2025 | 29.05.2025 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14 |  | 62.6 | 0.18 | 600 | PROJECT COMPLETED Lastest KPI : May 2025
25 | 5900991 | DECOMMISSIONING OF DEA DESULPHURIZATION SYSTEM IN AMM-1 | Probus / Fertil | Ossi Valto | 21.01.2025 | 21.06.2025 | 23.08.2025 | Ravikumar | 29 | 29 | 0 | 100% | Rev. D01 | 13.02.2025 | [14 empty] | 80.65 | 0 | 0 | Lastest KPI : May 2025
26 | 5901029 | Feasibility Study for SWD System & New Asphalt Roads in Buhasa | ADNOC Gas | Pravin Kumar | 04.02.2024 | 04.08.2024 | 19.09.2025 | Rajasekhar |  |  | 0 | #DIV/0! | Rev. C | 21.03.2025 | 25.04.2025 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7 |  | 48.4 | 1.05 | 0 | Lastest KPI : May 2025
27 | 5900616 | PROJECT NO: J736 UPGRADE RAW ETHANE EXPORT TO ADNOC REFINING & HEPTANE | ADNOC Gas | Pankaj Kumar | 11.08.2022 | 11.02.2023 | 30.07.2025 | Rajasekhar | 13 | 12 | 1 | 92.31% | Rev. C1 | 06.11.2022 | 23.12.2022 | [8 empty] | 7 | 0 | 0 | 31 | 100% |  | 1.06 | 1500 | Project was restarted at Aug 2025 Lastest KPI : Oct 2023
28 | 5901044 | Revamp of 801-C-001 Vacuum Distillation Unit at RR-III | DHAFIR / ADNOC Refining | Ossi Valto | 26.03.2025 | 26.06.2025 | 25.07.2025 | Rajasekhar | 53 | 49 | 4 | 92.45% | Rev. 0 | 30.04.2025 | 25.06.2025 | [5 empty] | 0 | 0 | 0 | 0 | 4 | 135 | 1 |  | 80.18 | 0 | 0 | Lastest KPI : May 2025
29 | 5901062 | Feasibility Study for the Conversion of Tank AT HFZT | ADNOC DISTRIBUTION | Pravin Kumar |  |  |  | Ravikumar |  |  | 0 | #DIV/0! | Rev. 0 | 24.04.2025 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7 |  |  | 0 | 0 | PROJECT COMPLETED
30 | 5901055 | ADOC-Detail Engineering for Mubarraz Redevelopment Project | ADOC (JAPAN) | Pravin Kumar | 25.04.2025 | 25.12.2025 |  | Ravikumar |  |  | 0 | #DIV/0! | Rev. 0 | 09.06.2025 | 28.08.2025 | 9.2025 | 10.2025 |  | 02.06.2025 |  | 0 | 1 | 110 | 0 | 4 | 110 | 9 |  | 37.62 | 0 | 2700 | Lastest KPI : May 2025
31 | 5901078 | Study for Ruwais NGL Trains 1 & 2 Sea Water Intake Limitation | ADNOC Gas | Aditya Kaushal | 09.05.2025 | 08.09.2025 | 08.10.2025 | Rajasekhar |  | 2 | -2 | #DIV/0! | Rev. 0 | 23.05.2025 | 21.07.2025 | 11.09.2025 |  |  |  |  | 0 | 0 | 0 | 0 | 12 | 148 | 0 |  | 81.37 | 0 | 0 | PROJECT COMPLETED
32 | 5901040 | New Fuel Depot at Mena Zayed Port | ADNOC DISTRIBUTION | Ossi Valto | 26.05.2025 | 08.09.2025 |  | Rajasekhar |  | 3 | -3 | #DIV/0! | Rev. 3 | 14.07.2025 | 04.08.2025 | [5 empty] | 0 | 0 | 0 | 0 | 7 | 134 | 0 |  | 67.21 | 0 | 0 | Project Closing Date is expired and client extention date was not recived. Shamma (Assisting)
33 | 5900764 | EPC WORKS FOR REPLACEMENT / UPGRADE OF WELLHEAD SCADA SYSTEM AT CCR, USSC | FALCOR / ADNOC OFFSHORE | Ossi Valto | 02.05.2025 | 08.05.2026 |  | Rajasekhar | 110 | 42 | 68 | 38.18% | Rev. 3 | 03.09.2025 | 25.09.2025 | 11.2025 | 3.2026 |  |  |  | 82 | [7 empty] | 23.92 | 0 | 0
34 | 5901079 | Reciprocating Compressor Pulsation Analysis Study | ADNOC Refining | Aarekh Mehrotra | 11.06.2025 | 11.12.2025 |  | Ravikumar |  |  | 0 | #DIV/0! | Rev. A | 14.07.2025 | [14 empty] | 26.6 | 0 | 0
35 | 5901110 | New Accommodation at Ettouk Island | ADNOC OFFSHORE | Ossi Valto | 02.06.2025 | 19.08.2025 |  | Rajasekhar |  |  | 0 | #DIV/0! | NA | [15 empty] | 96.97 | 0 | 0 | Project Closing Date is expired and client extention date was not recived.
36 | 5901056 | DETAILED ENGINEERING SERVICES FOR CENTRAL ENGINEERING DIVISION REMOTE CONTROL CENTER FOR ULL & UAD AT AL RUMAITHA (NEB) | ADNOC OFFSHORE | Pankaj Kumar | 10.07.2025 | 09.03.2026 |  | Rajasekhar |  |  | 0 | #DIV/0! | Rev. 2 | 04.09.2025 | 30.09.2025 | 29.12.2025 | 26.02.2026 |  |  |  | 175 | [7 empty] | 13.94 | 2.67 | 9300
37 | 5901142 | SARB PRODUCED WATER TREATMENT PROJECT | ADNOC OFFSHORE | Ossi Valto | 07.08.2025 | 06.04.2026 |  | Ravikumar |  |  | 0 | #DIV/0! | Rev 1 | 28.08.2025 | 30.10.2025 | 30.12.2025 | 27.02.2026 |  |  |  | 52 | [7 empty] | 4.48 | 0 | 600
38 | 5901112 | FLY CAMP OFFICE BUILDING | ADNOC OFFSHORE | [26 empty] | 0 | 0 | KOM is not yet attached in the Project Folder.
39 | 5901178 | REFUGEE SHELTERS | ADNOC OFFSHORE | [26 empty] | 0 | 0 | KOM is not yet attached in the Project Folder.
40 | 5901086 | T31-MOC -Upper Zakum Pkg 11 | ADNOC OFFSHORE | Muddaser Moazzam | 11.09.2025 | 11.07.2026 | [23 empty] | 0
41 |  | Project Management Consultancy (PMC) | ADNOC DISTRIBUTION | [26 empty] | 0
42 | 5901183 | Train 1 and 2 - Fire & Gas Detection System | Cegelec / ADNOC GAS | Ossi Valto | 25.09.2025 | 24.03.2025 |  | Rajasekhar | [21 empty] | 0
43 | 5901155 | Pre-FEED for Routing Regeneration Gas to Fuel Gas Header | ADNOC GAS | Aarekh Mehrotra | 29.09.2025 | 15.12.2025 |  | Rajasekhar | [21 empty] | 0
44 | 5901202 | FEED Ruwais Train 1 and 2 Facilities F & G Mapping | ADNOC GAS | Pravin Kumar | 18.11.2025 | 17.07.2025 |  | Rajasekhar
45 | 5901203 | SACS ENDORSEMENT FOR UAD
46 | 5901199 | Adequacy check of the existing Steam Drum (Tag No. 1600-D-004) for revised parameters
47 | 5901187 | BUNKERING WATER PUMPING SYSTEM FOR MOSB (ADNOC LOGISTICCS) | SSEC / ADNOC GAS | Ossi Valto |  |  |  | Rajasekhar
48 | 5901186 | NEW ACCOMODATION AT ASI AND UAAI ISLAND | ADNOC GAS | Ossi Valto |  |  |  | Rajasekhar

## Document Controller (hidden)
Sr No | RAD PROJECT NO | Project Name | Document Controller Name | Project Manager | Open / Closed
1 | 5900604 | FEED-ADOFF Engineering Framework for Zirku Package-1" | Mohamed Sultan | Mohamed Elbadry | Closed
2 | 5900666 | EPC FOR UPGRADE EXISTING GLYCOL FLARE IN BUHASA | Maybelline Cagatao | Nada Hassan (Handed over from Mohamed Elbadry) | Closed
3 | 5900434 | EDG & LV System Upgarde _Lower Zakum | Maharoof Uliyan | Mohamed Elbadry | Closed
4 | 5900712 | C&F FEED Study for Standalone Packaging Project | Maybelline Cagatao/ Ralston Rodrigues | Mohamed Elbadry | Closed
5 | 5900570 | Waste water Purification for Reuse FEED project | Maharoof Uliyan | Mohamed Elbadry | Closed
6 | 5900596 | ASAB 2 - DEMIN PACAKGE | Maybelline Cagatao | Pankaj Kumar | Closed
7 | 5900606 | SAHIL & HALIBA PROJECT |  | Pankaj Kumar | Closed
8 | 5900688 | FS_DE for Installation of Spare Ejectors_Flow meters | Maharoof Uliyan | Pankaj Kumar | Closed
9 | 5900647 | FEED for installation of Toxic Gas Detectors, MOL SS Replacement & Gas Header Dislocation | Dadhibal Lama | Pankaj Kumar | Closed
10 | 5900466 | Habshan_Bab Energy Efficiency improvement_Carbon Abatement Study |  | Pankaj Kumar | Closed
11 | 5900616 | ALBANNA - RW-FM UPGRADE PROJECT | Maybelline Cagatao | Pankaj Kumar | Hold
12 | 5900635 | GALAXY PIPELINE PROJECT | Maharoof Uliyan | Pravin Kumar | Open
13 | 5900590 | POTABLE & UTILITY WATER SYSTEM UPGRADE RSHT-2 (FEED) | Maharoof Uliyan | Pravin Kumar | Closed
14 | 5900485 | RSME PROJECT |  | Pravin Kumar | Closed
15 | 5900792 | Study for Flare Gas Recovery | Maharoof Uliyan | Pravin Kumar | Hold
16 | 5900643 | FEED Study to Implement Real Time AEMS at RR I II & III | Maharoof Uliyan | Nada Hassan | Closed
17 | 5900726 | FEED Study to Implement Real Time AEMS at Fertil | Maybelline Cagatao | Nada Hassan | Closed
18 | 5900813 | SATAH GIC Process & Corrosion Studies | Dadhibal Lama | Nada Hassan | Open
19 | 5900808 | SIL Revalidation for LNG Facilities at Das Island | Dadhibal Lama | Nada Hassan | Closed
20 | 5900702 | Sahil Phase III development | Mohamed Sultan | Mohd Sharique (Handed over from Mohamed Elbadry) | Open
21 | 5900738 | FEED + Engineering & Procurement Services and Construction Management (EPCM) for Grid Power Integration Project Das Island | Dadhibal Lama | Pankaj Kumar | Open
22 | 5900767 | Comprehensive Energy Review (Studies) | Maybelline Cagatao/ Ralston Rodrigues | Nada Hassan | Open
23 | 5900853 | FEED Study for Standalone Packaging Project (Phase 2) | Ralston Rodrigues | Muddaser | Closed
24 | 5900885 | HABSHAN & BAB TELECOM SYSTEMS UPGRADE PROJECT | Ralston Rodrigues | Pravin Kumar | Open
25 | 5900858 | TRANSIENT ANALYSIS STUDY FOR AL NOUF AND RUMAITHA P5 FACILITIES DEVELOPMENT | Maybelline Cagatao | Nada Hassan | Open
26 | 5900859 | STRESS ANALYSIS STUDY FOR AL NOUF & RUMAITHA P5 FACILITIES DEVELOPMENT | Maybelline Cagatao | Nada Hassan | Open
27 | 5900891 | Details Engineering for KEZAD Gas Network Phase 3 | Maharoof Uliyan | Muddaser | Open
28 | 5900828 | MIGRATION OF AVEVA MODELS TO SMART PLANT | Dadhibal Lama | Pankaj Kumar | Open
29 | 5900304 | Critical Electrical Upgradation at Das and Zirku | Mohamed Sultan | Nada Hassan (Handed over from Mohamed Elbadry) | Open
30 | 5900838 | FEED STUDY for AUTO-SAMPLER FOR SLD | Dadhibal Lama | Pankaj Kumar | Open
31 |  | Vital Infrastructure Project |  | Ossi Valto | Open
32 | 5900837 | DEBOTTLENECKING of STEAM CONDENSATE SYSTEM in HABSHAN – 5. | Maybelline Cagatao | Nada Hassan | Open
33 | 5900803 | FALCOR Battery Systems DAS Island Project | Maybelline Cagatao/ Ralston Rodrigues | Pravin Kumar | Open
34 | 5900737 | FEED for Upgrade of Train 1 & 2 Fire and Gas Detection System & F&G Mapping Study for LNG and ASR Trains | Maharoof Uliyan | Pravin Kumar | Open
35 | 5900921 | Operatoor Sheleter Improvement Project | Maybelline Cagatao | Ossi Valto | Open
36 | 5900892 | RUWAIS NGL TRAIN-3 FIRE & GAS DETECTION MAPPING IMPLEMENTATION | Maybelline Cagatao | Muddaser | Open
37 | 5900878 | FEED for C&F Instrument Air Piping Network Replacement / Upgrade at DAS island | Maharoof Uliyan | Nada Hassan | Open
38 | 5900486 | EPC WORKS FOR ESTIDAMA-SALES GAS PIPELINES NETWORK ENHANCEMENT- PACKAGE #1 | Maharoof Uliyan | Pankaj Kumar
39 | 5900585 | EPC for Fire Water Ring Replacement at MOT & MPS | Maharoof Uliyan | Pravin Kumar
40 | 5900620 | Provision of Engineering & Consultancy Services For Ethylene Vaporizer II In B2 -U&O |  | Mohamed Elbadry | Closed
41 | 5900366 | EPC For Flexibility Of Crude Oil Facilities At Fujairah Main Oil Terminal (MOT) |  | Pravin Kumar | Closed
42 | 5900389 | RUWAIS FIRE WATER NETWORK UPGRADE (NGL & SGP) | Maybelline Cagatao | Pravin Kumar
43 | 5900403 | CONSULTANCY SERVICES FOR EXTENDED FEASIBILITY / BASIC DESIGN FOR ENERGY REDUCTION AND OPTIMIZATION PROJECTS (8 NOS OF SCHEMES) AT RR-I, RR-II & RR-III |  | Pankaj Kumar | Closed
44 | 5900555 | BU HASA CDS FACILITIES CONSTRAINT STUDY |  | Pravin Kumar | Closed
45 | 5900617 | Engineering Study to Prepare The Construction Package For Fire Proofing Jackets For ESD Valve Actuators And MOVS At Ruwais Refinery-III |  | Muddaser | Closed
46 | 5900687 | TRANSIENT STUDY PERMANENT POTABLE WATER SUPPLY LINE TO SAHIL |  | Ramana Rao K.V. | Closed
47 | 5900653 | TRANSIENT STUDY FOR BUHASA WATER INJECTION CLUSTER LOOPING | Maybelline Cagatao | Pankaj Kumar
48 | 5900769 | Consultancy Services for FE Analysis for New nozzle arrangement for Product Receiver Tank & Purge Bin | Maybelline Cagatao | Nada Hassan | Closed
49 | 5900796 | FEED Study project for ASAB 0&3, 1&2 Burner Management Systems | Maybelline Cagatao/ Ralston Rodrigues | Pankaj Kumar
50 | 5900913 | RESIDUE YIELD IMPROVEMENT PROJECT | Maybelline Cagatao | Pankaj Kumar | Open
51 | 5900928 | STUDY & EVALUATION OF FLARE VENDOR PROPOSALS (ASAB-0 BURN PIT-B UPGRADE) | Dadhibal Lama | Pankaj Kumar | Open
52 | 5900942 | Upgradation works at AL AIN MP Depot and RAK Depot | Dadhibal Lama | Pravin Kumar | Open
53 | 5900899 | LASER SCAN & PROVISION OF FULL INTELLIGENT 3D MODELS FOR DAS ISLAND | Ralston Rodrigues | Naresh Nagpurkar | Open
54 | 5900927 | FEED-New Sewage Treatment Plant (STP) and PGU Demolition | Ralston Rodrigues | Pravin Kumar | Open
55 | 5900935 | FEED-BAB Miscellaneous Works-Package 1 | Dadhibal Lama | Pravin Kumar | Open
56 | 5900954 | STRESS ANALYSIS OF KS-1 SOL. PIPING & DET ENG FOR F1-UR-189 | Maybelline Cagatao | Nada Hassan | Open
57 | 5900978 | TRAIN 3 DECOUPLING MODIFICATIONS (APS) | Maybelline Cagatao | Ossi Valto | Open
58 | 5900982 | DIVERT EXCESS MP FUEL GAS-HABSHAN 0 | Maybelline Cagatao | Muddaser | Open
59 | 5900983 | H5 FLARES UPGRADE OF IGNITION AND DETECTION SYSTEMS | Maybelline Cagatao | Muddaser | Open
60 | 5900970 | Demolition of Tanks at Madinat Zayed Depot & RAK Depot | Dadhibal Lama | Pravin Kumar | Open
61 | 5900808 | SIL Revalidation for LNG Facilities at Das Island |  | Nada Hassan | Open
62 | 5900993 | HYDRAULICS –SURGE IMPULSE LOAD ANALYSIS | Maybelline Cagatao | Nada Hassan | Open
63 | 5900996 | STUDY ENERGY_PROCESS IMPROVEMENTS_SUSTAINABILITY INITIATIVES | Maybelline Cagatao | Pankaj Kumar | Open
64 | 5900949 | TSSA Provisions of O&M Pipelines Costing within AG Pipeline | Maharoof Uliyan | Ossi Valto | Open

## Sheet3 (hidden)
Audits (Extracted from Audit Schedules)
| 2024 | [11 empty] | 2025
# | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 |  |  | 5900738@ 30% Engg | 5900885@ 30% Engg | 5900891@ 30% Engg |  | 5900738@ 60% Engg | 5900878@ 30% Engg | 5900738@ 90% Engg | 5900878@ 60% Engg | 5900837@ 75% Engg | 5900878@ 90% Engg | 5900927@ 75% Engg | 5900935@ 75% Engg
2 | [6 empty] | 5900885@ 60% Engg |  | 5900837@ 25% Engg | 5900892@ 50% Engg | 5900885@ 90% Engg | 5900927@ 50% Engg | 5900982@ 60% Engg | 5900982@ 90% Engg
3 | [6 empty] | 5900891@ 60% Engg |  | 5900892@ 25% Engg | 5900978@ 30% Engg | 5900892@ 75% Engg | 5900935@ 25% Engg | 5900983@ 60% Engg | 5900983@ 90% Engg
4 | [8 empty] | 5900942@ 30% Engg |  | 5900927@ 25% Engg | 5900982@ 30% Engg
5 | [11 empty] | 5900983@ 30% Engg
6
7
8
9
10
Done
Was done in one audit rather than 2
Was not done

## Sheet2 (hidden)
Sr No | RAD PROJECT NO | COMPANY PROJECT No. | Project Name | CLIENT | Project Manager | Total No of Audits | No of Audits conducted | No of Audits - Pending | No of Audits - Scheduled | Audit Observation points - Status |  |  |  |  | Remarks
[10 empty] | Total No of Audit Observatio points | Complied /Closed | Audit - OPEN Points | Suggestion for improvement | No of CARs -OPEN
1 | 5900604 | 4700016843 | FEED-ADOFF Engineering Framework for Zirku Package-1" | ADNOC OFFSHORE | Mohamed Elbadry | 2 Nos. | 1 No.( Internal Audit - @25% of Engg.completion) | 1 No. | a) COMPANY Audit - 1 No. @ 50% - 60% of Engg.completion | 41 Nos. | 21 Nos. | 18 Nos. | 3 Nos. | OPEN - 2 Nos. / 2 Nos.
2 | 5900712 | 37001-00088 | C&F FEED Study for Standalone Packaging Project | BOROUGE | Mohamed Elbadry | 2Nos. | NIL | 2 Nos. | a) 1st Audit - July'23 @ 25% of Engg.Completion b) 2nd Audit - Aug'23 @ 50% - 60% of Engg.completion | N/A | N/A | N/A | N/A | N/A
3 | 5900590 | 5337 | EPC FOR UPGRADE EXISTING GLYCOL FLARE IN BUHASA | ADNOC GAS | Mohamed Elbadry | 2Nos. | 1 No.( Internal Audit - @50% of Engg.completion) | 1 No. | a) 2nd Audit - July'23 @ 75-80% of Engg.Completion | 10 Nos | 2 Nos. | 8 Nos. | NIL | OPEN - NIL / 1 No.
4 | 5900434 | AD312 | EDG & LV System Upgarde _Lower Zakum | ADNOC OFFSHORE | Mohamed Elbadry | 4 Nos. | 5 Nos. Audits conducted | 4 Nos. | a) Final Audit - Aug'23 @ 80% of Engg.Completion | 90 | 82 | 8 Nos. | 5 No. | OPEN - 1 No. / 4 Nos.
5 | 5900304 | 4700012103 | DAS EPC ELECTRICAL UP-GRADATION | ADNOC OFFSHORE | Mohamed Elbadry | 1 No. | NIL | 1 No. | a) Final Audit - July'23 @ 80% - 90% of Engg.Completion | N/A | N/A | N/A | N/A | N/A
[9 empty] | SUMMARY | 141 | 105 | 34 | 8 | 3

## sht1 (hidden)
RAD - PROJECT HANDOVER STATUS - 2023
Status as of 31.May.23
Sr No | RAD PROJECT NO | COMPANY PROJECT No. | Project Name | CLIENT | Project Manager |  |  | AUDITS |  | KPI Implementation | Status | Remarks
[6 empty] | PQP | Document Numbering Procedure | Internal Audit Report | COMPANY Audit |  | Part of MPR Reports
1 | 500389 | 0500839 | RUWAIS FIRE WATER NETWORK UPGRADE (NGL & SGP) | TARGET /ADNOC GAS PROCESSING | [6 empty] | CLOSED
2 | 500389 | 0500839 | RUWAIS FIRE WATER NETWORK UPGRADE (NGL & SGP) | TARGET /ADNOC GAS PROCESSING | [6 empty] | CLOSED
2 | 500389 | 0500839 | RUWAIS FIRE WATER NETWORK UPGRADE (NGL & SGP) | TARGET /ADNOC GAS PROCESSING | [6 empty] | CLOSED
3 | 500434 | P386/ 4700011289 | EPC WORKS FOR REPLACEMENT OF EMERGENCY DIESEL GENERATORS(EDGS) & LV SYSTEM UPGRADE AT LOWER ZAKUM. | CCTC/ ADNOC OFFSHORE | [6 empty] | CLOSED
4 | 500434 | P386/ 4700011289 | EPC WORKS FOR REPLACEMENT OF EMERGENCY DIESEL GENERATORS(EDGS) & LV SYSTEM UPGRADE AT LOWER ZAKUM. | CCTC/ ADNOC OFFSHORE | [6 empty] | CLOSED
5 | 500434 | P386/ 4700011289 | EPC WORKS FOR REPLACEMENT OF EMERGENCY DIESEL GENERATORS(EDGS) & LV SYSTEM UPGRADE AT LOWER ZAKUM. | CCTC/ ADNOC OFFSHORE | [6 empty] | CLOSED | Internally - NCR is closed, COMPANY given formal approval - Alvin.
6 | 500434 | P386/ 4700011289 | EPC WORKS FOR REPLACEMENT OF EMERGENCY DIESEL GENERATORS(EDGS) & LV SYSTEM UPGRADE AT LOWER ZAKUM. | CCTC/ ADNOC OFFSHORE | [6 empty] | CLOSED
7 | 5900486 | 1000483 | EPC WORKS FOR ESTIDAMA-SALES GAS PIPELINES NETWORK ENHANCEMENT- PACKAGE #1 | ISCCO/ADNOC GAS PROCESSING | [6 empty] | CLOSED
8 | 5900486 | 1000483 | EPC WORKS FOR ESTIDAMA-SALES GAS PIPELINES NETWORK ENHANCEMENT- PACKAGE #1 | ISCCO/ADNOC GAS PROCESSING | [6 empty] | CLOSED
9 | 5900486 | 1000483 | EPC WORKS FOR ESTIDAMA-SALES GAS PIPELINES NETWORK ENHANCEMENT- PACKAGE #1 | ISCCO/ADNOC GAS PROCESSING | [6 empty] | CLOSED
10 | 5900486 | 1000483 | EPC WORKS FOR ESTIDAMA-SALES GAS PIPELINES NETWORK ENHANCEMENT- PACKAGE #1 | ISCCO/ADNOC GAS PROCESSING | [6 empty] | CLOSED
11 | 5900486 | 1000483 | EPC WORKS FOR ESTIDAMA-SALES GAS PIPELINES NETWORK ENHANCEMENT- PACKAGE #1 | ISCCO/ADNOC GAS PROCESSING | [6 empty] | CLOSED
12 | 5900486 | 1000483 | EPC WORKS FOR ESTIDAMA-SALES GAS PIPELINES NETWORK ENHANCEMENT- PACKAGE #1 | ISCCO/ADNOC GAS PROCESSING | [6 empty] | CLOSED
11 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
12 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
13 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
14 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
15 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
16 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
17 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
18 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
19 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
20 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
21 | 500434 | P386/ 4700011289 | EPC WORKS FOR REPLACEMENT OF EMERGENCY DIESEL GENERATORS(EDGS) & LV SYSTEM UPGRADE AT LOWER ZAKUM. | CCTC/ ADNOC OFFSHORE | [6 empty] | CLOSED
22 | 500434 | P386/ 4700011289 | EPC WORKS FOR REPLACEMENT OF EMERGENCY DIESEL GENERATORS(EDGS) & LV SYSTEM UPGRADE AT LOWER ZAKUM. | CCTC/ ADNOC OFFSHORE | [6 empty] | CLOSED
23 | 5900366 | P24027 | MOT PROJECT | ADYARD/ ADNOC ONSHORE | [6 empty] | CLOSED
1 | 5900596 | 30001-50154 | ASAB 2 - DEMIN PACAKGE | ADNOC GAS | Nada Hassan / Pankaj Kumar | Rev - 0 - Approved by COMPANY | Rev - 0 - Approved by COMPANY | Submitted | CARs submitted. Observations are pending. | YES | YES - Shall be included in MPR from May'23 | Prepared for Apr'23 to May'23
2 | 5900643 | 00506 | FEED Study to Implement Real Time AEMS at RR I II & III | ADNOCREFINING | Nada Hassan | Rev 0 - Submitted on 29.May.23 COMPANY Approval is awaited. | COMPANY Numbering procedure being followed. | Scheduled on 07.June.23 | NIL | YES | YES - Shall be included in MPR from May'23
3 | 5900726 | 4900005966 | FEED Study to Implement Real Time AEMS at Fertil | FERTIL | Nada Hassan | Rev D01 - Submitted on 29.May.23 COMPANY Approval is awaited. | COMPANY Numbering procedure being followed. | Scheduled on 06.June.23 | NIL | YES | YES - Shall be included in MPR from May'23
4 | 5900635 | 58501 | GALAXY PIPELINE PROJECT | ADNOC GAS | Pravin Kumar | Rev 0 - Submitted on 10.May.23 COMPANY Approval is awaited. | COMPANY Numbering procedure being followed. | Scheduled on 31.May.23 | NIL | YES | YES - Shall be included in MPR from May'23
5 | 5900604 | 4700016843 | FEED-ADOFF Engineering Framework for Zirku Package-1" | ADNOC OFFSHORE | Mohamed Elbadry | Rev 0 - Submitted on 10.May.23 COMPANY Approval is awaited. | COMPANY Numbering procedure being followed. | Scheduled on 09.June.23 | Scheduled on July'23 | YES | YES - Shall be included in MPR from May'23 | Prepared for Apr'23
6 | 5900647 | PKG - 1 - P 12537 PKG - 2 - P 12538 PKG - 3 - P 12534 | FEED for installation of Toxic Gas Detectors, MOL SS Replacement & Gas Header Dislocation | ADNOC ONSHORE | Pankaj Kumar | PQP is under Preparation. Planned to submit on 07.June.23 | Document requests shared by Discipoine Leads to get the Document Serial Nos. | Scheduled on Aug'23 | Scheduled on Sep-Oct'23 | NO | YES - Shall be included in MPR from June'23 | New Project
7 | 5900688 | E1342 | FS_DE for Installation of Spare Ejectors_Flow meters | ADNOC OFFSHORE | Pankaj Kumar | COMPANY adsvised to use the Target PQP | Document requests shared by Discipoine Leads to get the Document Serial Nos. | Scheduled on July'23 | Scheduled on Sep-Oct'23 | NO | YES - Shall be included in MPR from June'23 | New Project
8 | 5900712 | BOR XXXXXX | C&F FEED Study for Standalone Packaging Project | BOROUGE | Mohamed Elbadry | Rev G - Submitted on 25.May.23 COMPANY Approval is awaited. | Document Serial Nos. assigned by COMPANY on 31.May.23 | Scheduled on July'23 | Scheduled on Aug'23 | YES | YES - Shall be included in MPR from May'23
9 | 5900570 | BOR200120 | Waste water Purification for Reuse FEED project | BOROUGE | Pravin Kumar | Rev H - Submitted on 10.Feb.23 COMPANY Approved in Code D . | Document Nos. assigned. However, COMPANY informed that they will assign the Document serial nos.based on the Existing document philosophy | Scheduled on 12.June.23 | NIL | YES | YES - Shall be included in MPR from May'23 | Prepared for Jan'23 to April'23
10 | 5900590 | 508209 | POTABLE & UTILITY WATER SYSTEM UPGRADE RSHT-2 (FEED) | ADNOC GAS | Pravin Kumar | Rev 0 - Submitted on 06.April.23 COMPANY has Approved it | Rev 0 - Submitted on 05.April.23 COMPANY has Approved it | Scheduled on June'23. Date to be discussed with Pravin | Scheduled on Aug'23 | YES | YES - Shall be included in MPR from May'23 | Prepared for Feb'23 to April'23
11 | 5900590 | 5337 | EPC FOR UPGRADE EXISTING GLYCOL FLARE IN BUHASA | ADNOC GAS | Mohamed Elbadry | COMPANY adsvised to use the 5337 PQP | COMPANY Numbering procedure being followed. | Audit conducted on 17.May.23 | CONTRACTOR conducted the Audit conducted on 19.May.23. Audit report is awaited | NO | YES - Shall be included in MPR from May'23

## Sheet1 (hidden)
Details of Findings
No | Activities Covered | ISO/PQP– Clause Ref | Records Checked & Procedures Witnessed | Status |  |  |  | Comments
|  |  |  | Major Non-conformance | Minor Non-conformance | Observation | OFI
(CARs # when raised)
1 | Quality Reporting system | Planning Package | The Recovery Plan for the delay beyond 10% has not been initiated and no official document submission to Company was evidenced during the Audit |  | X
2 | Quality Reporting system | PP-30001-50154-A2-216-51-00-001 | Actions have been required by the company but evidence to display the following actions are pending |  |  | X
|  | Clause 7.3 | a) Manpower (Mobilization chart and mom/demob)
b) previous items
c) Recovery plan
3 | Resources | PP-30001-50154-A2-216-51-00-001 | Letters have been sent by company and a response of more than 30 days have been provided by Rejlers initial 27 Feb and response 31 march |  |  |  | X
Clause 6.3
4 | Resources | PP-30001-50154-A2-216-51-00-001 | The Main scope of the project pertains to material & Manufacturing issues of the Material. There is no Material Engineer available for this Project and the Sub Contractor material Engineer who prepares the document on behalf of the Sub Contractor also reviews the document on behalf of the Engineer and there is no Review by Engineer |  | X
Clause 7.3
| Quality Reporting system | Exhibit B 4.3 | The contents of the Monthly and weekly report are not as per Exhibit 4.3 and exhibit B 10. Several data like Audit schedule (plan vs actual), lessons learnt Matrix etc are missing |  | X
5
Clause 6.2/6.3
6 | KPI | PP-30001-50154-A2-216-51-00-001 | Out of the 7 KPIs identified, 4 are not meeting the criteria and there is no mitigation or correction plan for these failed KPIs |  | X
Clause 6.2
7 | Quality Reporting system | PP-30001-50154-A2-216-51-00-001 | Non availability of exbibit requirements and documentation with the project members. The documentation should be available for better transfer and sharing of information. |  |  |  | X
Clause 7.4
8 | Review of Risk Register | PP-30001-50154-A2-216-51-00-001 | No major workshops conducted against plan. Actual vs plan (3 out 6 not conducted), Subcontractor register 50 % of workshop have not completed in time. 3 missed their deadlines. |  |  | X
Clause 11.6
9 | Review of Risk Register | PP-30001-50154-A2-216-51-00-001 | The risk register, item number 3 (Risk 6 B) after 6A. The mitigation is insufficient. The risk to be revisited for better evaluation. (Mitigated and reviewed) |  |  |  | X
Clause 8.3.2
10 | Review of Risk Register | PP-30001-50154-A2-216-51-00-001 | section 8.3.2. of the PQP mentions that risk review to be conducted on monthly basis. Instead, it should be reviewed on a quarterly basis. |  |  |  | X
Clause 8.3.2
11 | Deviation Control | PP-30001-50154-A2-216-51-00-001 | During IDC / SDC, documents have been sent for review to the reviewers. The review has happened, but no mechanism in place to track implementation of these comments. |  |  |  | X
Clause 6.3
12 | Design Verification | RACI Matrix | Process design basis the Rev has not passed by Rotating for IDC as per required by RACI. |  |  | X
13 | Review of Lesson learnt Register | PP-30001-50154-A2-216-51-00-001 | Master TC a new column should be present for reference document that incorporates the lesson learned in their tracking register. |  |  |  | X
Clause 12.3
Input planning package number